## Roadmap
BOB — Project Roadmap & Gantt ¦ Jun 2026 → Dec 2027 ¦ Tracker: stato, date, completamento, Track (owner)
# | Track | Owner | Task / Milestone | Status | Start | End | Done on | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
WEBSITE — CORE BUILD (DEMO) · Jun–Jul 2026
1 | Client/Pro | André | Webapp MVP — Next.js 14 + Supabase marketplace | Done | 2026-06-01 | 2026-06-15 | 2026-06-03
1.1 | Client/Pro | André | Project setup, Vercel deploy pipeline, Supabase schema + RLS | Done | 2026-06-01 | 2026-06-05 | 2026-06-03
1.2 | Client/Pro | André | Real auth + separate client / pro personal areas | Done | 2026-06-01 | 2026-06-10 | 2026-06-03
1.3 | Client/Pro | André | City pages (Milano live; Roma, Torino prepared) + 15 service categories | Done | 2026-06-05 | 2026-06-15 | 2026-06-03
2 | Client/Pro | André | AI concierge chat (Claude Haiku + rules fallback) | Done | 2026-06-01 | 2026-06-15 | 2026-06-03
2.1 | Client/Pro | André | Problem understanding via LLM with rules fallback | Done | 2026-06-01 | 2026-06-10 | 2026-06-03
2.2 | Client/Pro | André | Optional budget + multi-pro quote requests from chat | Done | 2026-06-05 | 2026-06-15 | 2026-06-03
3 | Client/Pro | André | Messaging + pro dashboard | Done | 2026-06-01 | 2026-06-15 | 2026-06-03
3.1 | Client/Pro | André | Bidirectional client-pro messaging | Done | 2026-06-01 | 2026-06-10 | 2026-06-03
3.2 | Client/Pro | André | Pro dashboard: calendar, hours, earnings | Done | 2026-06-05 | 2026-06-15 | 2026-06-03
3.3 | Client/Pro | André | Unread message badges in header (desktop + mobile) | Done | 2026-06-10 | 2026-06-15 | 2026-06-03
4 | Client/Pro | André | Chat v2 + client memory + job brief | Done | 2026-06-05 | 2026-07-08 | 2026-07-08
4.1 | Client/Pro | André | F1 agentic chat, F2 customer memory, F3 pro request summary | Done | 2026-06-05 | 2026-06-30 | 2026-06-09
4.2 | Client/Pro | André | Job brief v1: tool-use extraction, photo vision, recap card, subtask taxonomy | Done | 2026-07-01 | 2026-07-08 | 2026-07-08
5 | Internal | André | Admin panel | Done | 2026-06-28 | 2026-07-05 | 2026-07-04
5.1 | Internal | André | Pro verification, users management, CS accounts + roles | Done | 2026-06-28 | 2026-06-30 | 2026-06-28
5.2 | Internal | André | Delete users (cascade) + team invitations via email | Done | 2026-07-01 | 2026-07-05 | 2026-07-04
6 | Client/Pro | André | Technical SEO foundation | Done | 2026-07-01 | 2026-07-05 | 2026-07-04
6.1 | Client/Pro | André | Sitemap, robots.txt, JSON-LD structured data, optimized metadata | Done | 2026-07-01 | 2026-07-05 | 2026-07-04
7 | Client/Pro | André | Pro portfolio with tier gating + reviews + self-service profile | Done | 2026-07-01 | 2026-07-11 | 2026-07-11
7.1 | Client/Pro | André | Portfolio items + storage bucket + tier limits (Free/Pro/Business) | Done | 2026-07-01 | 2026-07-04 | 2026-07-04
7.2 | Client/Pro | André | Reviews: request close + ReviewDialog with RLS constraints (mig 015) | Done | 2026-07-08 | 2026-07-11 | 2026-07-11
7.3 | Client/Pro | André | Pro self-service profile /dashboard/profilo (mig 016) | Done | 2026-07-09 | 2026-07-11 | 2026-07-11
7b | Shared | Claude | Migrations backfill 001-017, CI (build+lint), RLS performance cleanup (018) | Done | 2026-07-16 | 2026-07-16 | 2026-07-16
CLIENT & PRO EXPERIENCE OVERHAUL · Jul 2026 (journey-map audit → build)
8 | Client/Pro | Claude | Client & pro journey audit + UX gap analysis | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.0 | Client/Pro | Claude | Full code+live audit, journey maps, prioritized gap list (Word doc) | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.1 | Client/Pro | André | Bob chat: draft persistence + returnTo login + inline city waitlist | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.2 | Client/Pro | André | Client journey st.1/3/5/6/7 | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.2a | Client/Pro | André | Header Bob CTA for clients, clickable coming-soon cities | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.2b | Client/Pro | André | Why-this-pro line, realtime messages (mig 019), URL sync, quote_request label | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.2c | Client/Pro | André | Close-request dialog, customer memory wired, client account page | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.3 | Client/Pro | André | Account v2 + saved addresses | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.3a | Client/Pro | André | Saved addresses (mig 020) + Bob address chips at city step | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.3b | Client/Pro | André | Old-password check, self-service email change, floating messages bubble | Done | 2026-07-17 | 2026-07-17 | 2026-07-17
8.4 | Client/Pro | André | Role-aware navigation + pro acquisition banner | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.4a | Client/Pro | André | Header nav client-only; unified Account button | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.4b | Client/Pro | André | Pre-footer pro banner (guests, public pages) | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.5 | Client/Pro | André | Client dashboard v2 + shared appointments | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.5a | Client/Pro | André | Attention strip, job timelines, trusted pros, collapsed history | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.5b | Client/Pro | André | Shared appointments (mig 021): pro proposes from chat, client confirms | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.6 | Client/Pro | André | Per-pro message threads + quote comparison (stage 4) | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.6a | Client/Pro | André | Thread per request-pro pair (mig 022), tightened RLS (no cross-pro leak) | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.6b | Client/Pro | André | Quote comparison in client dashboard; Bob brief + photos attached to request | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.7 | Client/Pro | André | Appointment negotiation v2 | Done | 2026-07-18 | 2026-07-19 | 2026-07-19
8.7a | Client/Pro | André | Free-slot engine; pro quick-pick slots + double-booking guard | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
8.7b | Client/Pro | André | Client counter-proposal within pro free slots (mig 023); Europe/Rome tz fix | Done | 2026-07-18 | 2026-07-19 | 2026-07-19
8.8 | Client/Pro | André | Mobile overflow fix (base grid-cols-1 on responsive grids) | Done | 2026-07-19 | 2026-07-19 | 2026-07-19
ANALYTICS, ADMIN & PRIVACY · Jul 2026
9 | Internal | Lucio | Admin overview / Analisi dashboard | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
9.1 | Internal | Lucio | KPI dashboard + signup age/terms + city geo hierarchy (mig 024) | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
9.2 | Internal | Lucio | Analisi: unified filters, subscription-tier events (mig 025), 2 new indicators | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
9.3 | Internal | Lucio | Analisi UI redesign, Excel export, cancellations view | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
9.4 | Internal | Lucio | 'Ricerche per categoria' anonymous search events (mig 026); staff redirect | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
25b | Internal | Lucio | Privacy: birth date + terms consent moved to private table (mig 027) | Done | 2026-07-18 | 2026-07-18 | 2026-07-18
WEBSITE — REMAINING TO GO-LIVE · Aug–Dec 2026
8.9 | Client/Pro | André | Empty / error / loading states + server-side validation pass | Planned | 2026-08-15 | 2026-09-30
10 | Client/Pro | André | Automated pro verification + verified badge | Planned | 2026-09-01 | 2026-10-31
10.1 | Shared | André | VIES / Agenzia Entrate P.IVA check integration | Planned | 2026-09-01 | 2026-09-30
10.2 | Internal | Lucio | ID document upload + manual review queue in admin | Planned | 2026-09-15 | 2026-10-15
10.3 | Client/Pro | André | Verified badge UI on profiles, listings and ranking; 48h SLA workflow | Planned | 2026-10-01 | 2026-10-31
11 | Client/Pro | André | Transparent ranking + Visibility Boost | Planned | 2026-10-01 | 2026-11-30
11.1 | Internal | Lucio | Ranking algorithm v1: response rate, closure rate, reviews (data logic) | Planned | 2026-10-01 | 2026-10-31
11.2 | Client/Pro | André | Ranking explanation UI (seeded by 'why this pro' line) | Planned | 2026-10-15 | 2026-11-15
11.3 | Client/Pro | André | Boost purchase + placement logic; quality floor | Planned | 2026-11-01 | 2026-11-30
12 | Client/Pro | André | Stripe billing — Pro EUR24/19, Business EUR59/49 | Planned | 2026-10-01 | 2026-12-31
12.1 | Client/Pro | André | Stripe products & prices; checkout + customer portal | Planned | 2026-10-01 | 2026-11-30
12.2 | Shared | André | Webhooks -> subscription_tier sync (replaces manual switch) | Planned | 2026-11-01 | 2026-11-30
12.3 | Client/Pro | André | Founding-pro coupon; failed payments, invoices, receipts | Planned | 2026-11-15 | 2026-12-31
13 | Client/Pro | André | SEO content engine (ongoing) | In progress | 2026-08-01 | 2027-12-31
13.1 | Client/Pro | André | Keyword plan from Semrush data | Done | 2026-07-01 | 2026-07-05 | 2026-07-05
13.2 | Client/Pro | André | City x service page template + Milano core categories | Planned | 2026-08-01 | 2026-10-31
13.3 | Client/Pro | André | 'Quanto costa' price guides; Roma+Torino pages before activation | Planned | 2026-10-01 | 2027-03-31
14 | Shared |  | Google Business Profile + local presence | Planned | 2026-11-01 | 2026-12-31
15 | Shared |  | Launch hardening | Planned | 2026-12-01 | 2026-12-31
15.1 | Shared |  | End-to-end QA of all flows (client, pro, admin) | Planned | 2026-12-01 | 2026-12-15
15.2 | Client/Pro | André | Performance / Core Web Vitals pass | Planned | 2026-12-01 | 2026-12-20
15.3 | Shared |  | Freelance security review (pre-launch) | Planned | 2026-12-01 | 2026-12-20
15.4 | Client/Pro | André | Activate email notifications (Resend): account, DNS/DKIM, env vars, deliverability test | Planned | 2026-12-01 | 2026-12-20
15.5 | Internal | Lucio | Error monitoring, uptime alerts, backups; go-live checklist + rollback | Planned | 2026-12-10 | 2026-12-31
Bx | Client/Pro | André | Email notifications pipeline — BUILT, DORMANT (activates with RESEND_API_KEY) | Done | 2026-07-19 | 2026-07-19 | 2026-07-19
LAUNCH & YEAR-1 PRODUCT · 2027
16 | Shared |  | GO-LIVE — Milano pilot | Milestone | 2027-01-01 | 2027-01-31
16.1 | Shared |  | Production cutover; activate founding pros (60-80) in 5 core categories | Planned | 2027-01-01 | 2027-01-31
16.2 | Shared |  | Bob Pro subscriptions live (Stripe) + Boost on; launch PR wave | Planned | 2027-01-01 | 2027-01-31
17 | Client/Pro | André | Unlimited requests (subscribers) + digital quotes | Planned | 2027-03-01 | 2027-06-30
17.1 | Client/Pro | André | Free-tier request limits + upgrade paywall | Planned | 2027-03-01 | 2027-04-15
17.2 | Client/Pro | André | Quote builder for pros + client quote comparison + accept flow | Planned | 2027-04-01 | 2027-06-30
18 | Shared |  | Security audit (gate before payments) | Planned | 2027-06-01 | 2027-07-31
19 | Client/Pro | André | Protected flow — payments + Garanzia Bob | Planned | 2027-07-01 | 2027-12-31
19.1 | Client/Pro | André | Stripe Connect: deposit/escrow, payouts; dispute + mediation tooling | Planned | 2027-07-01 | 2027-10-31
19.2 | Client/Pro | André | Verified reviews tied to protected jobs; 8% success fee billing | Planned | 2027-09-15 | 2027-11-15
20 | Shared |  | Roma + Torino activation | Planned | 2027-04-01 | 2027-06-30
21 | Shared |  | Bologna, Firenze, Napoli activation | Planned | 2027-07-01 | 2027-12-31
22 | Shared |  | National infrastructural opening (organic only) | Planned | 2027-10-01 | 2027-12-31
LEGAL & BUREAUCRACY
23 | Shared |  | Site legal docs (ToS, privacy, cookie + consent banner) + lawyer review | Planned | 2026-09-01 | 2026-11-30
24 | Shared |  | Trademark 'Bob' (UIBM/EUIPO, classes 35, 42) | Planned | 2026-09-01 | 2026-10-31
25 | Shared |  | GDPR full compliance | Planned | 2026-11-01 | 2027-01-31
25.1 | Internal | Lucio | Registro trattamenti + retention policy; consent flows audit; breach procedure | Planned | 2026-11-01 | 2027-01-31
25.2 | Shared |  | DPAs with processors (Supabase, Vercel, Anthropic, Stripe, Resend) | Planned | 2026-11-15 | 2026-12-31
26 | Shared |  | SRL incorporation (Q1 Year 1) | Planned | 2026-12-01 | 2027-02-28
27 | Shared |  | Finanza agevolata application (Q2 Year 1) | Planned | 2027-04-01 | 2027-06-30
28 | Shared |  | Garanzia Bob legal framework + payments compliance (Stripe Connect KYC) | Planned | 2027-05-01 | 2027-09-30
GO-TO-MARKET & MARKETING
30 | Shared |  | Founder outreach — first 100 Milano pros | Planned | 2026-10-01 | 2027-03-31
31 | Shared |  | Launch incentives (3 months free Bob Pro for founding pros) | Planned | 2027-01-01 | 2027-03-31
32 | Shared |  | Paid ads ignition — Milano only (CAC < EUR25 Q1) | Planned | 2027-01-01 | 2027-06-30
33 | Shared |  | PR launch ('AI concierge that fights lavoro nero') | Planned | 2027-01-01 | 2027-03-31
34 | Shared |  | Pro referral program + territorial partnerships | Planned | 2027-03-01 | 2027-12-31
KPI GATES (decision checkpoints)
36 | Internal | Lucio | End-Q1 2027: 60-80 active pros, 150+ req/mo, match >60% | Milestone | 2027-03-01 | 2027-03-31
37 | Internal | Lucio | End-2027: 600 pros, 1,500 req/mo, 25% protected-flow, CAC < EUR15 | Milestone | 2027-12-01 | 2027-12-31
LEGENDA
|  |  | Done (verde) |  |  | Track: Client/Pro → André (esperienza cliente e professionista)
|  |  | In progress (blu) |  |  | Track: Internal → Lucio (dati, dashboard, admin, privacy)
|  |  | Planned (grigio) |  |  | Track: Shared (infra, legale, GTM, milestone)
Milestone / gate (ambra)
Fonte dati: roadmap.csv (modificalo e rilancia build_roadmap.py). Le barre si disegnano da Status+Start+End; 'Done on' = data di completamento effettiva. Mese corrente evidenziato in rosso. Email notifiche: pronte ma DORMIENTI fino al task 15.4.